## Planner
June - August	Status		Notes
		Decide Dates of MAP (Feb-April)	March XX, 2024-March YY, 2024

		Book Visiting Artists
			Visiting Artist Name	Email	Phone	Notes (starting time preference, meal time length etc.)

		Reserve Venue, check on condition of piano.
			Venue	Venue Contact Name	Email	Address	Phone	Booked Date	Rent	Notes

		Contact Info for Piano Technicians (if needed)	Name	Phone	Email		Tuning Appt	Cost

September
		Set MAP Registration Deadline	January XX, 2024	**Avoid Dec 22-Jan 2

		Announce MAP in Chapter Meetings & Newsletters	Include:
			- MAP dates
			- Visiting Artists
			- Venues
			- Registration deadline
			- MTNA/WSMTA membership must be paid by Oct 15 (or Jan 10 for new members).
			- MAP grant available at the following link:		https://wsmta.org/music-artistry-program-grant-information-and-application/

		Pick up MAP certificates at Leadership Seminar

October
		Announce MAP in Chapter Meetings & Newsletters
		Preliminary Report Due Nov 1	Preliminary Report is located at WSMTA website under Member Dashboard after login
			https://wsmta.org/member-dashboard/adjudications-preliminary-report/
		Decide Date for Scheduling Party	(If your chapter uses a committee of teachers to prepare MAP schedule).
			MAP Schedule is due at least 5 weeks before the event.

November
		Announce MAP in Chapter Meetings & Newsletters
		Get in touch with Visiting Artist	Remind:
			- Dates
			- Contact info for hotels nearby
			- Will be in touch after the schedule is prepared.
			- Ask Visiting Artist for bios if needed.

December
		Announce MAP in Chapter Meetings & Newsletters
		MAP Registration open

		Prepare teacher schedule email	include
			- Teacher Information & Schedule Form
			- Student Evaluation Form
			- Legal Copy Verification
			- Request for Excused Absence

January
		Prepare schedule!	Please use new Excel Template	https://wsmta.org/wp-content/uploads/2023/08/MAP-Scheduling-Sheet_2023-2024.xlsx
			Due at least 5 weeks before MAP event.
			MAP Registration Report Link:	https://wsmta.org/map/reports/
			- requires Login. Report link is also under Member Dashboard.

		Check with Visiting Artist	Confirm dates, starting time of each day, preference of lunch period.

		Email Schedule to Jason for approval

	Once Schedule is approved:

		Apply for Event Liability Insurance	Login mtna.org, paste in the following link:		https://www.mtna.org/MTNA/Connect/Affiliate_Services/General_Liability_Request_Form.aspx
			If you do not have mtna login, you may also fill out the following form and request Jason to apply on your behalf
			https://forms.gle/W9YE7KcEqwJdMoC4A

		Confirm with venue the MAP dates	Request venue checks from your chapter treasurer.
			TAKE A PICTURE for Final Report before giving the checks to venues.

		Send MAP schedule to teachers

February
		Venue walkthrough	Arrange key pick-up, payment

		Confirm with Visiting Artists	*Transportation Needs? Snacks during the day? Lunch with teachers? Motel preferences?

MAP
		Meet with Visiting Artist at/before Orientation
		Meet with Visiting Artist at Closing Conference	Present Paycheck.

After MAP
		Send in the student names for State Honors Recital	Link:	https://wsmta.org/state-recital-representatives/
		Remind teachers to fill out Visiting Artist Evaluation online	Link:	https://wsmta.org/adjudicator-evaluations/
		File Final Report before May 1	Final Report is located at:	https://wsmta.org/8792-2/
			WSMTA only reimburses Chapter for venue/tuning at max of $125/8 hours.
			All other expense reeimbursement (lunch with Visiting Artist, supplies, etc.) should be filed with your chapter treasurer.

## MAP Form Links
For MAP Chairs
	2023-2024 Visiting Artist List	https://wsmta.org/2023-2024-visiting-artist-list/
	2023-2024 MAP Booklet	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2023/07/2023-2024-MAP-Booklet.pdf
	2023-2024 Chapter Chair Procedure	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2023/07/MAP-2023-24-Chapter-Chair-Procedures.pdf
	Visiting Artist Work Agreement	https://wsmta.org/wp-content/uploads/2017/09/MAP-Visiting-Artist-working-agreement-2017-2018.docx
	Visiting Artist Contract	https://wsmta.org/wp-content/uploads/2017/07/MAP-Visiting-Artist-Contract-with-Chapters.doc
	MAP Schedule Form **New**	https://wsmta.org/wp-content/uploads/2023/08/MAP-Scheduling-Sheet_2023-2024.xlsx
	High School Credit Form for VA	No longer needed. Jason will include student names in the event schedule sent to VA.

	Teacher Written Consultation Form	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2022/02/Teacher-Written-Eval-form.pdf

For Teachers
	2023-2024 MAP Booklet	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2023/07/2023-2024-MAP-Booklet.pdf
	MAP Fee Grant Application	https://wsmta.org/music-artistry-program-grant-information-and-application/
	Registration Worksheet	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2017/09/MAP-Registration-Worksheet.pdf

	Teacher Information and Student Schedule
	(1 page)	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2017/09/MAP-Teacher-Info-and-Student-Schedule-1-page.pdf
	(3 pages)	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2017/09/MAP-Teacher-Info-and-Student-Schedule-3-pages-1.pdf
	Student Evaluation Form
	(PDF)	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2017/09/MAP-Student-Evaluation-WEB.pdf
	(Word)	https://wsmta.org/wp-content/uploads/2021/01/2021-MAP-Student-Evaluation-Form.docx
	Legal Copy Verification	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2013/09/LEGAL-COPY-VERIFICATION-form.pdf

	Request for Excused Absence	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2017/09/MAP-Request-for-Excused-Absence-WEB.pdf

	2024 Certificate of Achievement	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2023/07/Certificate_Achievement_2023-2024_fillable.pdf
	2024 Certificate of Participation	https://y3e3n2z4.stackpathcdn.com/wp-content/uploads/2023/07/Certificate_Participation_2023-2024_fillable.pdf

## Participating Teachers
First Name	Last Name	Email	Phone	# of Students	Chapter Fee Due	Chapter Fee Paid	Time Slot Request	Time Slot Assigned

## Volunteers
First Name	Last Name	Email	Phone	Tasks	Date	Time	Notes